## Schedule
Section | When / Time | What / Block
Timeline (overview) | Now (Sep 2026) | Venue scouting starts. Outline due to Roger and Sandra 2026-09-04
Timeline (overview) | Mid to late Sep 2026 | Topic selection decision by Skat and SDC
Timeline (overview) | Mid-Oct 2026 | Preparatory day back-to-back with the AGUASAN meeting
Timeline (overview) | Autumn 2026 | Budget clarification with Skat and SDC: is there a possibility to provide a participant support line and/or childcare line
Timeline (overview) | Mid-October to end of November 2026 | SNSF Scientific Exchanges application for participant support submitted, with participants unnamed and the selection process described (allowed under the guidelines; travel capped at CHF 1,000 per unnamed participant); the decision takes up to three months, so it lands before the February outreach
Timeline (overview) | Winter 2026/27 | Steering Group design sessions (per the AGUASAN process)
Timeline (overview) | ~1 to 14 Feb 2027 | Outreach and promotion campaign, a two-week push
Timeline (overview) | ~Mid-March 2027 | Outreach reminder 1 (four weeks after the campaign)
Timeline (overview) | ~Mid-April 2027 | Outreach reminder 2 (eight weeks after the campaign)
Timeline (overview) | Beginning of May 2027 (~Mon 3 May) | Submission due date: participation applications plus grant and travel bursary requests (six weeks before selection concludes)
Timeline (overview) | May to mid-June 2027 | Screening: datasets, surveys, videos; selection decisions
Timeline (overview) | Mid-June 2027 | Participant selection concludes, before Swiss summer school holidays and leaving enough time for invitations and visas. Precourse window opens
Timeline (overview) | Mid-June to end of August 2027 | Precourse window: each group of six meets online with its supporter; dataset review for sensitive fields before anything is shared; targeted support with data collection tools where a participant's data calls for it; accounts and setup
Timeline (overview) | By ~30 Aug 2027 (one week before start) | Precourse work completed by every participant: accounts created, setup worked through, a clean browser with the relevant bookmarks, precourse assignments read
Timeline (overview) | Week of 6 to 10 Sep 2027 | Workshop week
Timeline (overview) | Within two weeks after (by ~24 Sep 2027) | "Data Science for openwashdata 003", the 10-week online course starts: the immediate follow-up course. Output potential: Journal style articles with participants data.
Timeline (overview) | By ~end of October 2027 | Evaluation survey results and the custodian workshop report delivered in the requested format; the recommendations report drafted with the Steering Group
Timeline (overview) | March 2028 and September 2028 | Impact monitoring at six and twelve months; the research article follows the twelve month point (both proposed)
Timeline (overview) | May/June or September/October 2028 (to decide) | Second openwashdata conference at Monte Verità (Congressi Stefano Franscini); application in preparation, due 2026-10-31 (to confirm on the CSF platform)
Monday | Until 10:30 | Arrival buffer: the first two hours are parked because not everyone can travel on weekends
Monday | 10:30 to 11:00 | Opening
Monday | 11:00 to lunch | One module: Git / GitHub Foundations
Monday | 13:00 to 15:00 | Two modules: Git / GitHub foundations, one hour each
Monday | 15:00 to 16:30 | Case study, discussions, buffer
Monday | 16:30 | Close
Tuesday | 08:30 to 09:00 | Arrival block
Tuesday | 09:00 to 11:00 | Two modules: GitHub Task & Project Management
Tuesday | 11:00 to 12:00 | Data project work
Tuesday | 13:00 to 15:00 | FAIR data principles and responsible sharing, with work sessions on the participants' own data
Tuesday | 15:00 to 16:30 | Case study, discussions, buffer
Tuesday | 16:30 | Close
Wednesday | 08:30 to 10:30 | Morning walk with a walking case-study debrief; the teaching side runs through all the work so far and identifies progress in each project
Wednesday | 10:30 to 12:00 | Agentic AI, first module: concepts and a first hands-on run with an agent on the participant's own package
Wednesday | 13:00 to 15:00 | Agentic AI, modules two and three, including data security with agents
Wednesday | 15:00 to 16:30 | Personal project work with agentic AI
Wednesday | 16:30 | Close
Wednesday | Evening | Walk, run, fire. Topic: AI disruption of the workplace
Thursday | 08:30 to 09:00 | Arrival block
Thursday | 09:00 to 10:30 | Selected participants share their in-workshop work as case studies, invited on the basis of the Wednesday progress review
Thursday | 10:30 to 12:00 | Personal project work with agentic AI, taking up what the morning presentations inspired
Thursday | 13:00 to 14:00 | Data management strategy: what a strategy outline or plan for the participant's own organization contains, and the approach for drafting it
Thursday | 14:00 to 15:00 | Work session: draft the outline or plan with an agentic skill workflow (a packaged, reusable workflow for an AI agent that drafts from the participant's data package and a short questionnaire)
Thursday | 15:00 to 16:30 | Case study, discussions, buffer
Thursday | 16:30 | Close
Friday | 08:30 to 09:00 | Arrival block
Friday | 09:00 to 11:30 | Quarto website workshop (the RDMSS workshop, slightly extended to 2.5 hours; see References)
Friday | 13:00 to 14:00 | AI session: craft the personal website and publish it (for participants who brought their CVs to the morning workshop)
Friday | 14:00 to 15:00 | Closing session: the week summarized through the outputs that were created, the evaluation survey completed in the room, and commitment confirmed for the coming R data science class (Data Science for openwashdata 003)
Friday | 15:00 | Close, end of the week